## Gantt
Smart Parking Platform – Draft Project Timeline (Gantt) – v2.0, Sep 17 2026
Editable: Duration (working days) and People per task; Start dates are formulas driven by predecessors (FS = finish-to-start, SS = start-to-start). Bars redraw automatically.
[10 empty] | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr
ID | Task / Deliverable | Team | People | Story pts | Duration (wd) | Start | End | Predecessors | Phase | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28 | 2027-01-04 | 2027-01-11 | 2027-01-18 | 2027-01-25 | 2027-02-01 | 2027-02-08 | 2027-02-15 | 2027-02-22 | 2027-03-01 | 2027-03-08 | 2027-03-15 | 2027-03-22 | 2027-03-29 | 2027-04-05 | 2027-04-12
M0 | Project kickoff / contract award (SRS v1.0) | PM |  |  | 0 | 2026-09-08 | 2026-09-08 |  | Milestone
M1 | Requirements & Design Approved | Client + PM |  |  | 0 | 2026-10-16 | 2026-10-16 | P0.2 FS | Milestone
M2 | MVP Acceptance (40% payment milestone) | Client + PM |  |  | 0 | 2027-02-17 | 2027-02-17 | C1 FS | Milestone
M3 | Beta Release (all 14 facilities, invited drivers) | Client + PM |  |  | 0 | 2027-03-03 | 2027-03-03 | T2 FS | Milestone
M4 | Final Delivery & Handover (30% payment milestone) | Client + PM |  |  | 0 | 2027-04-05 | 2027-04-05 | C2 FS | Milestone
P0.1 | Requirements finalization (SRS v1.0 -> v3.0, use cases, NFRs) | PM + leads |  |  | 24 | 2026-09-08 | 2026-10-09 | M0 FS | Phase 0
P0.2 | Architecture, data model and UX design | Leads + UX |  |  | 20 | 2026-09-21 | 2026-10-16 | P0.1 SS | Phase 0
1 | Accounts, Authentication & Security |  |  | 50 |  | 2026-11-04 | 2026-12-14 |  | Module summary
1.1 | Driver Accounts | Backend + Web | 3 | 13 | 9 | 2026-11-04 | 2026-11-16 | 8.1 FS | MVP scope
1.2 | Operator & Administrator Access Control | Backend + Web | 3 | 15 | 10 | 2026-11-17 | 2026-12-02 | 1.1 FS | MVP scope
1.3 | Fraud & Abuse Prevention | Backend | 2 | 11 | 11 | 2026-11-30 | 2026-12-14 | 4.1 FS, 1.1 FS | Beta scope
1.4 | Data Protection & Audit | Backend | 2 | 11 | 11 | 2026-11-17 | 2026-12-03 | 1.2 SS | Beta scope
2 | Availability, Map & Navigation |  |  | 33 |  | 2026-11-20 | 2026-12-10 |  | Module summary
2.1 | Real-Time Availability Engine | Backend + Mapping | 3 | 13 | 9 | 2026-11-20 | 2026-12-04 | 8.2 FS | MVP scope
2.2 | Facility Search & Map | Mapping + Mobile | 4 | 15 | 8 | 2026-11-20 | 2026-12-03 | 8.4 FS, 2.1 SS | MVP scope
2.3 | Navigation Hand-off | Mobile | 2 | 5 | 5 | 2026-12-04 | 2026-12-10 | 2.2 FS | MVP scope
3 | Reservations & Permits |  |  | 43 |  | 2027-01-05 | 2027-02-03 |  | Module summary
3.1 | Reservation Engine | Backend + Mobile | 4 | 21 | 11 | 2027-01-05 | 2027-01-20 | 5.2 FS, 2.2 FS, 4.1 FS | MVP scope
3.2 | Active Session Management | Backend + Mobile | 3 | 8 | 6 | 2027-01-27 | 2027-02-03 | 3.3 FS | Beta scope
3.3 | Entry Credentials | Backend + Mobile | 3 | 6 | 4 | 2027-01-21 | 2027-01-26 | 3.1 FS, 8.2 FS | MVP scope
3.4 | Monthly Permits | Backend + Mobile | 3 | 8 | 6 | 2027-01-21 | 2027-01-28 | 3.1 FS | Beta scope
4 | Payments, Receipts & Finance |  |  | 37 |  | 2026-11-04 | 2027-02-10 |  | Module summary
4.1 | Payment Processing | Payments | 2 | 16 | 16 | 2026-11-04 | 2026-11-25 | 8.1 FS | MVP scope
4.2 | Receipts & History | Payments + Mobile | 3 | 5 | 4 | 2027-01-21 | 2027-01-26 | 3.1 FS | Beta scope
4.3 | Finance Tools | Payments + Web | 3 | 16 | 11 | 2027-01-27 | 2027-02-10 | 4.2 FS | Beta scope
5 | Operator Dashboard & Facility Management |  |  | 46 |  | 2026-12-03 | 2027-02-04 |  | Module summary
5.1 | Facility Configuration | Web + Backend | 3 | 12 | 8 | 2026-12-03 | 2026-12-14 | 1.2 FS | MVP scope
5.2 | Pricing | Web + Backend | 3 | 16 | 11 | 2026-12-15 | 2027-01-04 | 5.1 FS | MVP scope
5.3 | Occupancy Monitoring | Web + Backend | 3 | 8 | 6 | 2026-12-15 | 2026-12-22 | 2.1 FS, 5.1 FS | Beta scope
5.4 | Reservation Management & Lane Assist | Web + Backend | 3 | 10 | 7 | 2027-01-27 | 2027-02-04 | 3.3 FS | Beta scope
6 | Reporting & Analytics |  |  | 19 |  | 2026-12-07 | 2027-02-09 |  | Module summary
6.1 | Operator Reports | Backend + Web | 3 | 14 | 10 | 2027-01-27 | 2027-02-09 | 4.2 FS, 5.3 FS | Beta scope
6.2 | Open Data | Backend | 2 | 5 | 5 | 2026-12-07 | 2026-12-11 | 2.1 FS | Beta scope
7 | Notifications |  |  | 12 |  | 2026-11-04 | 2026-11-20 |  | Module summary
7.1 | Notification Service | Backend | 2 | 11 | 11 | 2026-11-04 | 2026-11-18 | 8.1 FS | MVP scope
7.2 | Preferences | Mobile | 1 | 1 | 2 | 2026-11-19 | 2026-11-20 | 7.1 FS | MVP scope
8 | Hardware Integration & Platform Infrastructure |  |  | 64 |  | 2026-10-19 | 2026-12-10 |  | Module summary
8.1 | Cloud Platform | Backend/API | 3 | 18 | 12 | 2026-10-19 | 2026-11-03 | M1 FS | MVP scope
8.2 | Gate & LPR Integration | Backend/API | 3 | 18 | 12 | 2026-11-04 | 2026-11-19 | 8.1 FS | MVP scope
8.3 | Facility Edge Service | Backend/API | 2 | 13 | 13 | 2026-11-20 | 2026-12-10 | 8.2 FS | MVP scope
8.4 | Client Application Shells | Mobile + Web | 4 | 15 | 8 | 2026-10-19 | 2026-10-28 | 8.1 SS | MVP scope
9 | Quality Assurance & Release |  |  | 52 |  | 2026-10-19 | 2027-03-17 |  | Module summary
9.1 | Test Infrastructure | QA | 2 | 21 | 21 | 2026-10-19 | 2026-11-16 | 8.1 SS | MVP scope
9.2 | Performance, Security & Usability Validation | QA | 3 | 16 | 11 | 2027-01-27 | 2027-02-10 | 3.3 FS, 8.3 FS | Beta scope
9.3 | Release Management | QA + PM | 3 | 15 | 10 | 2027-03-04 | 2027-03-17 | M3 FS | Release
T1 | MVP integration & end-to-end testing (2 pilot facilities, gate/LPR, payments) | QA + all teams |  |  | 10 | 2027-01-27 | 2027-02-09 | 3.3 FS, 2.3 FS, 8.3 FS | Phase 1 – MVP build
C1 | Schedule cushion – MVP (5 working days) | — |  |  | 5 | 2027-02-10 | 2027-02-17 | T1 FS | Phase 1 – MVP build
T2 | Beta regression, stress-test run and security sign-off | QA + Backend |  |  | 10 | 2027-02-18 | 2027-03-03 | 9.2 FS, 6.1 FS, 4.3 FS | Phase 2 – Beta build
C2 | Schedule cushion – Final (13 working days) | — |  |  | 13 | 2027-03-18 | 2027-04-05 | 9.3 FS | Phase 3 – Release
Legend: ■ blue = MVP-scope deliverable ■ green = Beta-scope deliverable ■ amber = integration / E2E test window ■ grey = schedule cushion ■ red = milestone ■ purple = requirements & design
Durations = ROUNDUP(story points × days-per-point ÷ people). Blue cells on this and the Assumptions sheet are the inputs; everything else recalculates.

## Assumptions
Smart Parking Platform – Schedule Assumptions (v2.0 draft, HW2)
Assumption | Value | Note
Days per story point (blended developer-days) | 2 | 1 SP ≈ 2 developer-days incl. code review, unit tests, sprint ceremonies. Edit to re-time every task.
Build start (first working day after design approval) | 2026-10-19 | Day after milestone M1
Cushion – MVP (working days) | 5 | Novice-domain cushion; lecture 3 recommends 15–20% total
Cushion – Final (working days) | 13
Integration/E2E test window (working days) | 10 | Applied before MVP and Beta milestones
Team (from SRS §2.3; sizes assumed, unlimited budget)
Team | People
Backend/API | 6
Mobile Application | 3
Web Application | 3
Mapping & Location | 2
Payment Integration | 2
QA & Testing | 3
Project Manager | 1
Total | 20
Non-working days (holidays) – used by WORKDAY()
2026-11-26
2026-11-27
2026-12-24
2026-12-25
2026-12-31
2027-01-01
2027-01-18
2027-02-15
Legend: blue text / yellow fill = editable input. Change a duration or the days-per-point value and all dependent dates and bars update.

## WBS
WBS ID | Level | Deliverable / Work item | Story points | Rationale / trace to SRS
1 | 1 | Accounts, Authentication & Security | 50 | FR-1–FR-4, FR-26, NFR-7/8/15; UC-1, UC-18
1.1 | 2 | Driver Accounts | 13
1.1.1 | 3 | Email/password registration with verification code | 3 | UC-1 steps 1–2; standard but touches email service
1.1.2 | 3 | Apple and Google sign-in (OAuth) | 5 | Two third-party identity providers, app-store review rules
1.1.3 | 3 | Vehicle profiles (up to 5, default vehicle, plate-ownership check) | 3 | FR-2; CRUD plus duplicate-plate exception
1.1.4 | 3 | Password reset and account recovery | 2 | Well-understood pattern
1.2 | 2 | Operator & Administrator Access Control | 15
1.2.1 | 3 | Role and permission model (Operator Admin, Facility Manager, Finance, Attendant, Platform Admin) | 5 | FR-3; permissions scoped per facility
1.2.2 | 3 | Staff invitation and facility assignment | 3 | UC-18 steps 1–2
1.2.3 | 3 | Multi-factor authentication and 30-minute session expiry | 5 | FR-4, NFR-8; MFA provider integration
1.2.4 | 3 | Immediate session and API-token revocation on user removal | 2 | UC-18 exception
1.3 | 2 | Fraud & Abuse Prevention | 11
1.3.1 | 3 | Bot and duplicate-account defenses (rate limiting, CAPTCHA, device checks) | 5 | Lecture 3 'bot army' risk; unknowns in tuning
1.3.2 | 3 | Verified payment method with name match required before first reservation | 3 | Depends on 4.1; policy logic
1.3.3 | 3 | Per-account reservation limits and no-show rules | 3 | Business rules plus enforcement
1.4 | 2 | Data Protection & Audit | 11
1.4.1 | 3 | Encryption in transit (TLS 1.2+) and at rest (AES-256), key management | 3 | NFR-7; mostly configuration
1.4.2 | 3 | Personal-data export and deletion tools | 3 | NFR-15; touches every data store
1.4.3 | 3 | Audit log service with before/after values (12-month retention) | 5 | FR-26; cross-cutting hook into all admin actions
2 | 1 | Availability, Map & Navigation | 33 | FR-5–FR-8, NFR-1/2; UC-2, UC-4
2.1 | 2 | Real-Time Availability Engine | 13
2.1.1 | 3 | Occupancy counter service consuming gate and sensor events | 8 | NFR-2 5-second freshness; concurrency and event ordering risk
2.1.2 | 3 | 'Last updated' staleness tracking and degraded-mode flag | 2 | A-1 fallback
2.1.3 | 3 | Waitlist notification when no availability | 3 | UC-2 exception
2.2 | 2 | Facility Search & Map | 15
2.2.1 | 3 | Map provider integration (Google Maps Platform / Mapbox) and geocoding | 5 | A-4; secondary provider fallback
2.2.2 | 3 | Search by destination or current location with arrival time and duration | 5 | UC-2 steps 1–2; NFR-1 2-second target
2.2.3 | 3 | Filters (price, distance, covered, EV, height, 24/7) and list view | 3 | FR-5
2.2.4 | 3 | Facility detail page (photos, hours, entrance instructions) | 2 | UC-2 step 4
2.3 | 2 | Navigation Hand-off | 5
2.3.1 | 3 | Deep link to Google Maps, Apple Maps and Waze with entrance coordinates | 3 | FR-8; three platforms
2.3.2 | 3 | In-app fallback directions and entrance description | 2 | UC-4 exception
3 | 1 | Reservations & Permits | 43 | FR-9–FR-13, NFR-9/13; UC-3, UC-6, UC-7, UC-9
3.1 | 2 | Reservation Engine | 21
3.1.1 | 3 | Inventory hold and double-sell prevention | 8 | FR-10; core transactional logic, highest business risk
3.1.2 | 3 | Hourly, daily and event booking flow with all-in price display | 5 | UC-3; NFR-9 4-tap flow
3.1.3 | 3 | Cancellation-policy engine and automatic refund calculation | 5 | FR-11; per-facility policies
3.1.4 | 3 | Modify or cancel reservation flow | 3 | UC-7
3.2 | 2 | Active Session Management | 8
3.2.1 | 3 | Session extension with capacity check and additional charge | 5 | UC-6, FR-12
3.2.2 | 3 | Overstay rate handling and nearby alternatives | 3 | UC-6 exception
3.3 | 2 | Entry Credentials | 6
3.3.1 | 3 | QR code generation with offline caching | 3 | FR-13, NFR-13
3.3.2 | 3 | License-plate registration for LPR authorization | 3 | FR-13; links to 8.2
3.4 | 2 | Monthly Permits | 8
3.4.1 | 3 | Permit purchase with auto-renewal terms | 5 | UC-9; recurring billing
3.4.2 | 3 | Permit waitlist and 7-day renewal reminders | 3 | UC-9 exception
4 | 1 | Payments, Receipts & Finance | 37 | FR-14–FR-16, NFR-16; UC-8, UC-16, UC-17
4.1 | 2 | Payment Processing | 16
4.1.1 | 3 | Payment-provider integration (card tokenization, PCI scope kept at provider) | 8 | A-3, FR-14; third-party API, webhooks, failure modes
4.1.2 | 3 | Apple Pay and Google Pay | 5 | Two wallet integrations with platform certification
4.1.3 | 3 | Saved payment methods and failed-payment retry (5-minute hold release) | 3 | UC-3 exception
4.2 | 2 | Receipts & History | 5
4.2.1 | 3 | Itemized receipt generation (in-app, email, PDF) | 3 | FR-15, UC-8
4.2.2 | 3 | Reservation history with 24-month retention | 2 | FR-15
4.3 | 2 | Finance Tools | 16
4.3.1 | 3 | Refund workflow with reason, actor and second approval above limit | 5 | UC-16, FR-16
4.3.2 | 3 | Daily settlement reconciliation against provider settlement file | 8 | UC-17; file matching, discrepancy handling
4.3.3 | 3 | Export to accounting system | 3 | UC-17 step 4
5 | 1 | Operator Dashboard & Facility Management | 46 | FR-17–FR-20; UC-11, UC-12, UC-13, UC-15
5.1 | 2 | Facility Configuration | 12
5.1.1 | 3 | Add, edit and remove facility (address, capacity, hours, restrictions, amenities, entrance coordinates) | 5 | FR-17, UC-11
5.1.2 | 3 | Photo and entrance-instruction upload | 2 | UC-11 step 3
5.1.3 | 3 | Hardware credential linking, connection test and draft state | 5 | UC-11 steps 4–5 and exception
5.2 | 2 | Pricing | 16
5.2.1 | 3 | Rate schedules (hourly, daily, event, monthly) including taxes and fees | 5 | FR-18, UC-12
5.2.2 | 3 | Dynamic-pricing rules with floor, ceiling and occupancy/event triggers | 8 | FR-18; rules engine, high risk of edge cases
5.2.3 | 3 | Price preview and effective-date handling for existing reservations | 3 | UC-12 steps 4–5 and exception
5.3 | 2 | Occupancy Monitoring | 8
5.3.1 | 3 | Live facility and portfolio occupancy dashboard with 24-hour trend | 5 | FR-19, UC-13
5.3.2 | 3 | Threshold alerts and optional pause of same-day reservations | 3 | UC-13 steps 3–4
5.4 | 2 | Reservation Management & Lane Assist | 10
5.4.1 | 3 | Reservation search and manual override with audit trail | 5 | FR-20
5.4.2 | 3 | Lane-assist view for attendants including drive-up sale | 5 | UC-15
6 | 1 | Reporting & Analytics | 19 | FR-21, FR-25; UC-14
6.1 | 2 | Operator Reports | 14
6.1.1 | 3 | Occupancy, revenue and utilization reports by facility, date range and rate type | 8 | FR-21, UC-14; aggregation queries over large data
6.1.2 | 3 | CSV and PDF export | 3 | FR-21
6.1.3 | 3 | Scheduled weekly email summary | 3 | FR-21
6.2 | 2 | Open Data | 5
6.2.1 | 3 | Anonymized, aggregated occupancy feed for city transportation departments | 5 | FR-25; anonymization rules
7 | 1 | Notifications | 12 | FR-22, FR-23; UC-10
7.1 | 2 | Notification Service | 11
7.1.1 | 3 | Multi-channel delivery service (push, SMS, email) | 5 | Three providers, retry logic
7.1.2 | 3 | Driver event templates (confirmation, arrival reminder, 30/10-minute expiry, receipt) | 3 | FR-22
7.1.3 | 3 | Operator integration-health alerts after 5 minutes of silence | 3 | FR-23
7.2 | 2 | Preferences | 1
7.2.1 | 3 | Notification preference screen (per-channel, per-event toggles) | 1 | UC-10 — BASELINE: simplest item in the WBS
8 | 1 | Hardware Integration & Platform Infrastructure | 64 | FR-24, NFR-3/4/5/6/12/14; A-1, A-2; UC-5
8.1 | 2 | Cloud Platform | 18
8.1.1 | 3 | Cloud environment, containers, managed relational database and message queue | 8 | Foundation for everything; NFR-6 scaling design
8.1.2 | 3 | CI/CD pipeline and dev/stage/prod environments | 5 | Enables interleaved testing
8.1.3 | 3 | Monitoring, logging and uptime alerting | 5 | NFR-4 99.9%/99.95% targets
8.2 | 2 | Gate & LPR Integration | 18
8.2.1 | 3 | Public API and webhook specification for entry/exit events and entry authorization | 5 | FR-24; documentation deliverable
8.2.2 | 3 | Pluggable vendor adapters for gate controllers and LPR cameras | 8 | NFR-14, A-2; unknown vendor behaviour
8.2.3 | 3 | Sub-1-second entry authorization path | 5 | NFR-3, UC-5 gate entry; performance-critical
8.3 | 2 | Facility Edge Service | 13
8.3.1 | 3 | Local event buffering (24 hours) and synchronization on reconnect | 8 | NFR-5, A-1; distributed-systems risk
8.3.2 | 3 | Occupancy sensor ingestion | 5 | FR-7
8.4 | 2 | Client Application Shells | 15
8.4.1 | 3 | iOS application shell and App Store setup | 5 | NFR-12
8.4.2 | 3 | Android application shell and Google Play setup | 5 | NFR-12
8.4.3 | 3 | Responsive web SPA shell with accessibility baseline (WCAG 2.1 AA) | 5 | NFR-11/12
9 | 1 | Quality Assurance & Release | 52 | NFR-6/10/11/14; A-5
9.1 | 2 | Test Infrastructure | 21
9.1.1 | 3 | Unit-test framework with 80% coverage gate in CI | 5 | NFR-14; runs from sprint 1 (lecture: unit tests as safety net)
9.1.2 | 3 | Integration test suite (payments, hardware adapters, notifications) | 8 | Third-party sandboxes, hardware simulators
9.1.3 | 3 | End-to-end device test suite (iOS, Android, web) | 8 | Device farm, three platforms
9.2 | 2 | Performance, Security & Usability Validation | 16
9.2.1 | 3 | Stress-test harness (10,000 concurrent users, 500 facilities) | 8 | NFR-6; lecture: 'stress test harness' before launch
9.2.2 | 3 | Security review, PCI-scope confirmation and penetration test | 5 | NFR-7; external firm
9.2.3 | 3 | Accessibility and usability testing (8 of 10 first-time users) | 3 | NFR-10/11
9.3 | 2 | Release Management | 15
9.3.1 | 3 | Pilot at two client facilities with beta feedback loop | 5 | Lecture: iterate on real feedback before big-bang launch
9.3.2 | 3 | Client facility data onboarding (14 facilities) and staff training | 5 | A-5 two-week data buffer
9.3.3 | 3 | Production launch, app-store publication and handover documentation | 5 | Final delivery milestone
|  | TOTAL STORY POINTS | 356
Story points are relative (Fibonacci 1-2-3-5-8-13) and weigh complexity, risk and effort against baseline item 7.2.1 = 1 SP. Blue cells are editable.